## DDR#09
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 9
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-13
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / HAMZA / ADNAN |  |  | MD/TVD @ 00:00HRS: |  | 580 / 580 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 8.9792
RIG REP.: |  | TARIQ BUTT / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 580 / 580 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2019-05-12 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | SPUD MUD |  | HOLE SIZE (IN) |  |  |  | BIT No. |  |  |  | BHA No. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME | 12:00 | 23:45 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 676.05
DEPTH, MD (M) |  | 580 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER | [14 empty] | PITS (BBL) | 437
MW IN (SG) |  | 1.1 | DAILY PROGRESS (M) |  |  |  | TYPE | [14 empty] | ACT. SYS (BBL) | 1113.05
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. | [14 empty] | RESV. SYS (BBL) | 400
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE | [14 empty] | KILL MUD (BBL) | 400
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES | [14 empty] | KILL MW (SG) | 1.6
µ FUNNEL (SEC) |  | 55 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) | [14 empty] | TOTAL | 1513.05
PV |  | 9 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) | [14 empty] | DIESEL (LTR)
YIELD POINT |  | 19 | FLOWRATE (GPM) |  |  |  | METERAGE (M) | [14 empty] | RIG TANK | 107587
GEL ST. |  | 9/15 | PRESSURE (PSI) |  |  |  | RPM SURF. | [14 empty] | CAMP TANK | 25460
WL (ml/30 min.) |  | 9.5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 4640
CT ( in/32) |  | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED
ALK (MUD) |  |  | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 133047
ALK (FILT.) |  |  | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH |  | 9 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 470000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 90000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 308100
KCl (mg/l) |  | 3050.7 | JAR |  | NMDC |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 328100
CHLORIDES (mg/l) |  | 1500 | MOTOR |  | STAB - 1 |  | TFA (IN²) | [14 empty] | TOTAL
HARDNESS (mg/l) |  | 240 | 11'' DCS |  | STAB - 2 |  | HSI | [14 empty] | POB
OIL% |  |  | 9 1/2" DCS |  | SPSA |  | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [10 empty] | MPCL | 4
SAND % |  |  | BHA ROT. HRS |  |  |  | BIT No. |  |  |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 33
SOLIDS % |  | 7.92 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY | 5
M.B.T. (lb/bbl) |  | 20 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 56
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 100 | 2 X 100 |  | 30" CONDUCTOR |  |  | 37 | [11 empty] | TOTAL | 129
DAILY WELL COST (US$) |  | 266129 | SHAKER-2 | 1 X 50 | 2 X 50 |  | 20'' SURFACE/ K-55, 133# |  |  | 579 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 1552527 | SHAKER-3 | 1 X 100 | 2 X 100 | [16 empty] | LAST CSG SIZE
% OF AFE SPENT |  | 7.799% | MUD CLEANER | 3 X 140 | [17 empty] | LOT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR |  |  |  | P-1 - F-1600HL | 7 |  | 12" | 3430 PSI | 97% |  | 0.1385 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS |  |  |  | P-2 - F-1600HL | 7 |  | 12" | 3430 PSI | 97% |  | 0.1385 | [7 empty] | NAGRI | SURFACE
FIRE DRILL | 2019-05-09 | 2019-06-08 | BLIND RAMS |  |  |  | P-3 - F-1600HL | 7 |  | 12" | 3430 PSI | 97% |  | 0.1385 | [7 empty] | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD
TRIP DRILL |  |  | LAST BOP TEST DATE |  |  |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | BRINE LOSSES IN 24 HRS |  |  |  |  | BRINE LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL |  |  | NEXT BOP TEST DATE |  |  |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-05-12
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43597 | 43597.0625 | 1.5 | DRL | PT-P | CIR | CONT'D CIRCULATION TO CONDITION MUD MEANWHILE PREPARED MIX FLUID FOR CMT JOB.
43597.0625 | 43597.0729 | 0.25 | DRL | PT-P | SM | HELD PJSM, DISCUSSED SAFETY ABOUT 20'' CSG CEMENTATION.
43597.0729 | 43597.0938 | 0.5 | DRL | PT-P | P/T | R/UP DOWELL LINES AND CONNECTED SAME WITH RIG PUMPS & DOWELL UNIT. FLUSHED DOWELL LINES WITH FRESH WATER, CLOSED VALVE AND P/TESTED SAME AT 500/4000 PSI, OK.
43597.0938 | 43597.25 | 3.75 | DRL | PT-P | CMC | PUMPED 300 BBL LO-VIS PILL FOLLOWED BY 100 BBL MUDPUSH II SPACER OF 12 PPG. WITH RIG PUMP @ 10 BPM. SWITCHED OVER TO CEMENT UNIT & PUMPED 580 BBL FLY MIXED LEAD SLURRY OF 13.5 PPG @ 5-6 BPM. OBSERVED SPACER CONTAMINATION AFTER PUMPING 480 BBL OF LEAD SLURRY, OBSERVED NEAT CMT SURFACED AFTER PUMPING 580 BBL, STOPPED PUMPING LEAD SLURRY AND SWITCHED OVER TO FLY MIXED 150 BBL TAIL SLURRY OF 15.8 PPG @ 5-6 BPM. DISPLACED CEMENT WITH 5 BBL SPACER + 30 BBL MUD. STOPPED PUMPING & CHECKED BACK FLOW - NO BACK FLOW. DUMPED RETURNS DURING CMT JOB. NO LOSSES OBSERVED DURING JOB.
43597.25 | 43597.2917 | 1 | DRL | PT-P | WOC | R/DOWN DOWEL HOOK UP & CIRCULATING SUB. PULLED BACK 5-1/2" DP TO 475M. FLUSHED STRING WITH 30 BBL MUD
43597.2917 | 43597.4375 | 3.5 | DRL | PT-P | WOC | POOH TO SURFACE. L/ DOWN 5" PUP JOINT; 5" X20 " CENTRALIZER & STINGER- R/D DIVERTER VENT LINE UNDER RIG FLOOR.
43597.4375 | 43597.6875 | 6 | DRL | PT-P | WOC | MADE ARRANGEMENTS TO R/D FLOW LINE & RISER PIPE & DIVERTER. REMOVED MOUSE HOLE. DISMANTELED DIVERTER VENT LINE.
43597.6875 | 43597.75 | 1.5 | DRL | PT-P | CC | CUT TWO WINDOWS AT 30'' CONDUCTOR. ROUGH CUT 20'' CSG. L/DOWN LANDING JOINT, ELEVATOR AND SLIPS.
43597.75 | 43597.875 | 3 | DRL | PT-P | NDB | R/DOWN DIVERTER, FLOW LINE & RISER PIPE.
43597.875 | 43598 | 3 | DRL | PT-P | CC | CUT & L/DOWN 30" CONDUCTOR FROM CELLAR BASE. FINAL CUT 20" CASING AT 0.90M. GROUND / DRESSED & BEVELED 20" CASING STUB.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-05-13
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43598 | 43598.0833 | 2 | DRL | PT-P | WOC / | INSTALLED, LEVELED & LOCKED (20" SOL X 21 1/4" - 5K) CHH ON 20" CASING STUB. P/TESTED CHH @ 900 PSI & HELD PRESS FOR 10 MIN -OK.
43598.0833 | 43598.25 | 4 | DRL | PT-P | NUB | N/UP BOP IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | N/UP BOP IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | PERFORMED 20'' CSG CMT JOB AS PER PROGRAM, WOC.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | WOC, MEANWHILE CUT CSG, INSTALL AND TEST WELL HEAD, N/UP BOP, BOPT, M/UP 5 1/2'' DP STANDS FOR UPCOMING SECTION.
REMARKS |  |  | RELEASED W.FORD TRS CREW + TOOLS.
Formulas:
MIRAJ-1 = [SPUD MUD]+30